## Gantt
Design and Development of an AI-Enabled Smart EV Charging and Energy Management Platform
Project Gantt, September 2026 to June 2027 ¦ baseline of 24 October 2026 ¦ work packages and interfaces from the repository, milestones from the FYP handbook, month spans are planning judgements
Sub-project | Work package | Sep-26 | Oct-26 | Nov-26 | Dec-26 | Jan-27 | Feb-27 | Mar-27 | Apr-27 | May-27 | Jun-27 | Status, 24 Oct 2026
SP1 Data & forecasting | Data sourcing, licence check, dataset register | [10 empty] | Done
| Session-to-hourly demand pipeline | [10 empty] | Done
| Features, direct multi-horizon models, 25-origin backtest | [10 empty] | Done
| Cross-site validation, Palo Alto, no retuning | [10 empty] | Done, 0.549 vs 0.670
| Contract export and integration with SP2/SP4/SP5 | [10 empty] | In progress
| Interim report and presentation | [10 empty] | Draft
| Phase-3 evaluation support | [10 empty] | Planned
| Dissertation and final poster | [10 empty] | Planned
SP2 Smart scheduling | Tariff sources and cost model (issue #2) | [10 empty] | Sources verified, table pending
| Scheduler build: LP / heuristic against valley filling | [10 empty] | Planned
| Uncontrolled versus scheduled comparison | [10 empty] | Planned
| Phase-3 scenarios with SP1 | [10 empty] | Planned
SP3 Renewable-aware | Owner allocation and dataset decision | [10 empty] | Unallocated - risk
| Solar forecast module, ERA5 / NASA POWER | [10 empty] | Planned, at risk
SP4 Dashboard | Initial dashboard script (on fork, not merged) | [10 empty] | On fork, 99 lines
| Wire the contract files, replace placeholder columns | [10 empty] | Planned
| Views, integration test, reporting | [10 empty] | Planned
SP5 System assessment | Cost and carbon-intensity baseline for both sites | [10 empty] | Not started
| Savings, emissions and benchmarking | [10 empty] | Planned
| Final assessment report for the dashboard | [10 empty] | Planned
Milestones (programme handbook)
| Project Specification & Preliminary Report |  | ◆ | [8 empty] | 30 Oct 2026
| Interim Report |  |  |  |  | ◆ | [5 empty] | 8 Jan 2027
| Interim Presentation |  |  |  |  | ◆ | [5 empty] | 11-22 Jan 2027
| Final Poster | [7 empty] | ◆ |  |  | 19-21 Apr 2027
| Final Dissertation | [7 empty] | ◆ |  |  | 30 Apr 2027
| Project end (task book) | [9 empty] | ◆ | 1 Jul 2027
Reading the chart: a filled cell marks a month in which the work package is active.
Owners are taken from the sub-project READMEs; SP3 is still unallocated and is shown as a risk.
SP1 bars marked Done are evidenced by the merged pipeline, the 77 passing tests and the Phase-1 report.
SP4's September bar records an initial dashboard script that exists only on a fork, not in the main repository.
Consumers and producers of every arrow are fixed in docs/integration-contract.md.
Nothing in the repository records which month a work package runs: the bars are a baseline schedule derived from the deliverable dates, and may be moved without changing the plan's content.

## Milestones
Date | Milestone | Weight / note
30 Oct 2026 | Project Specification & Preliminary Report | 10% of the final mark
8 Jan 2027 | Interim Report | assessed
11-22 Jan 2027 | Interim Presentation | window set by the school
19-21 Apr 2027 | Final Poster | assessed
30 Apr 2027 | Final Dissertation | main submission
1 Jul 2027 | Project end | task-book end date